## Blad1
Date | Work Hours | Work Description
2017-05-07 | 8 | Set up GitHub directory, v0.1 READ ME and Timesheet. Started working on comments/code efficiency.
2017-06-07 | 8 | Worked on comments and code efficiency.
2017-07-07 | 8 | Improved FileOpener readability and efficiency.
2017-08-07 | 0 | Weekend
2017-09-07 | 0 | Weekend
2017-10-07 | 8 | Finished comments & summaries, added Doxygen code documentation to Git repository. Emailed Riemer about the direction of the project.
2017-11-07 | 8 | Worked on READ ME and Instructions.
2017-12-07 | 2 | Fixed hour proposition & Emailed Riemer and Anders about meeting.
13/7/2017 | 0 | Waiting for info from Riemer & Anders
14/7/2017 | 8 | Meeting with Riemer & Anders, License, Started working on the Interactive Tree View
15/7/2017 | 0 | Weekend
16/7/2017 | 0 | Weekend
17/7/2017 | 8 | Worked on tab selection and disabling editing when not in the editor tab.
18/7/2017 | 8 | Fixed some bugs with editing disabling and tab selection
19/7/2017 | 8 | Added scrollable tree view & branch item prefab
20/7/2017 | 8 | Worked on branch item prefab
21/7/2017 | 4 | Meeting with Riemer, waited for library updates
22/7/2017 | 0 | Weekend
23/7/2017 | 0 | Weekend
24/7/2017 | 0 | Waited for library updates
25/7/2017 | 2 | Waited for library updates & copy pasted license into code (received confirmation from Paul)
26/7/2017 | 4 | Downloaded library updates & looked through example
27/7/2017 | 0 | Vacation
28/7/2017 | 0 | Vacation
29/7/2017 | 0 | Vacation / Weekend
30/7/2017 | 0 | Vacation / Weekend
31/7/2017 | 0 | Vacation
2017-01-08 | 0 | Urgent side project
2017-02-08 | 0 | Urgent side project
2017-03-08 | 0 | Urgent side project
2017-04-08 | 0 | Urgent side project
2017-05-08 | 0 | Weekend
2017-06-08 | 0 | Weekend
2017-07-08 | 8 | Worked on manual & prototype
2017-08-08 | 8 | Worked on tree example prototype
2017-09-08 | 8 | Worked on tree example prototype
2017-10-08 | 8 | Worked on tree example prototype & emailed Riemer for clarification
2017-11-08
2017-12-08 | 0 | Weekend
13/8/2017 | 0 | Weekend
14/8/2017
Total:
124